## Slide 1
DIVISION PROGRAM IMPLEMENTATION REVIEW AND PERFORMANCE ASSESSMENT
CY 2025 1ST QUARTER
April 10, 2025
SDO Iriga City Teachers’ Hall

## Slide 2
SECTION: | Curriculum Implementation Division (CID)
Head: | JERSON V. TORALDE Chief ES

## Slide 3
INTERMEDIATE OUTCOMES PERFORMANCE INDICATORS (per DepEd Oder No. 29, s. 2022 – Agency Performance Measurement Matrix)

## Slide 4
Program, project and activities
(continuing 2024)

## Slide 5
EQUITY
IO: Disadvantaged school-age children and youth, and adults benefited from appropriate equity initiatives

## Slide 6
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
SPED (Special Education Program-SNED) | No. of Schools Offering the program | 41 | 41 | 100% | N/A
 | No. of Enrolment | 397 | N/A | N/A | N/A
 | No. of Activities Conducted | 1 | 1 | 100% | Conducted February 2025
IPEd (Indigenous Peoples Education Program) | No. of Schools Offering the program | 43 | N/A | N/A | N/A
 | No. of Enrolment | 1626 | N/A | N/A | N/A
 | No. of Activities Conducted | 3 | 3 | 100% | Completed last January and February 2025
 | No. of Schools with program support funds (PSF) received | N/A | N/A | N/A | N/A

## Slide 7
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
MG (Multigrade Education Program) | No. of Schools Offering the program | 2 | 2 | 100% | N/A
 | No. of Enrolment | 123 | 123 | 100% | 
 | No. of Activities Conducted | 1 | 1 | 0.00% | one activity was conducted last 2024 and another activity will be conducted this Q2
ALS (Alternative Learning System) | No. of Schools Offering the Program | 42 CLCs | N/A | N/A | N/A
 | No. of Enrolment | 1500 | N/A | N/A | N/A
 | No. of Activities Conducted | 15 | N/A | N/A | N/A
 | No. of ALS teachers with paid transportation and teaching aid allowance |  |  |  | 
 | No. of CAIs teachers with paid transportation and teaching aid allowance | N/A |  |  | 
MEP (Madrasah Education Program) | No. of Schools Offering the Program | 1 |  |  | 
 | No. of Enrolment | 58 |  |  | 
 | No. of Asatidz paid |  |  |  | 
 | No. of Activities Conducted |  |  |  | Already conducted in 2024

## Slide 8
Quality
IO: Learners complete K-12 basic education, having successfully attained all learning standards that equip them with the necessary skills and attributes to pursue their chosen paths

## Slide 9
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
Learning Tools Equipment (LTE) – Science and Mathematics (SM) | No. of tools and equipment delivered | 1 | 0 | 0.00% | Ongoing process of the documents such as PPMP, WFP, Project proposal, etc.
 | No. of learners benefiting the program | 3 schools SJIS, SPNHS, ICSHS | 0 | 0.00% | To be distributed in Q3

## Slide 10
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
Learning Tools Equipment (LTE) – Tech-Voc and Livelihood(TVL) Equipment | No. of tools and equipment delivered |  | 0 | 0.00% | It was obligated by the ZAHS Accountant and to be procured this Q2
 | No. of learners benefiting the program | 400 | 0 | 0.00% | It was obligated by the ZAHS Accountant and to be procured this Q2
ELLN (Early Language Literacy and Numeracy) | No. of Activity Conducted | 1 | N/A | N/A | 100% conducted in 2024
 | No. of teachers trained | 105 | N/A | N/A | 100% ELLN Trained Teachers

## Slide 11
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
Textbooks (and Other Instructional materials) | No. of schools provided with textbooks/instructional materials | 51 | 51 | 100.00% | All schools have been provided by Textbooks/IMs
NASBE (National Assessment Systems for Basic Education ) | No. of National Assessments conducted | 3 | 1 | 33.33% | No ELLNA and NAT G12
 | No. of Activities conducted | 1 | 0 | 0.00% | To be implemented this Q2
FLO (Flexible Learning Options) | No. of Schools Provided with Learning Resources | 2 | N/A | N/A | Accomplished last 2024

## Slide 12
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
ADM (Alternative Delivery Mode) | No. of Activities Conducted | 1 | 0 | 0.00% | Obligated and ready for implementation this Q3
ALSADM (Implementation of Alternative Learning and Delivery Mode Programs, including requirement of Learning Centers) | No. of Activities Conducted | N/A | N/A | N/A | N/A
 | No. of materials procured | N/A | N/A | N/A | N/A
 | No. of training/seminars/conferences attended | N/A | N/A | N/A | N/A
Journalism | No. of students participated in the National Press Conference | N/A | N/A | N/A | Fully accomplished in 2024
 | No. of Activities Conducted | N/A | N/A | N/A | Fully conducted in 2024

## Slide 13
resiliencY and well-being
IO: Learners are resilient and know their rights and have the life skills to protect themselves and claim their education-related rights from DepEd and other duty-bearers to promote learners’ well-being.

## Slide 14
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
BEC (Basic Education Curriculum) | No. of learners participated in the activity (NLC) | 6240 | 6240 | 100% | Learners actively participated the NLC
 | No. of Schools participated | 48 | 48 | 100% | All schools had participated the NLC
 | No. of teachers paid for their meal allowances | 374 | 374 | 100% | Teachers have been paid for their meal allowances
 | No. of capacity building/orientation conducted | 4 | 4 | 100% | 100% Capacity Building/Orientation have been conducted
 | No. of learning materials procured/produced | 18720 | 18720 | 100% | Learners were given LMs

## Slide 15
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
NASBE (National Assessment Systems for Basic Education ) | No. of National Assessments conducted | 3 | 1 | 33.33% | Only Grade 6 NAT was conducted
 | No. of Activities conducted | N/A | N/A | N/A | N/A

## Slide 16
KEY PERFORMANCE INDICATORS AND Program, project and activities
(Current- 2025)

## Slide 17
EQUITY
IO: Disadvantaged school-age children and youth, and adults benefited from appropriate equity initiatives

## Slide 18
Performance Indicators | SY 2022-2023 | SY 2023-2024 | SY 2024-2025 | Reasons for Under/Over Performance
Elementary Gender Parity Index Completion | 1.00 | 1.01 | 1.02 | The trend reveals that there is parity between sexes
Secondary Gender Parity Index Completion | 1.02 | 1.10 | 1.10 | The trend reveals that there is parity between sexes
KPIs (Three-Year Data)

## Slide 19
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
SPED (Special Education Program-SNED) | No. of Schools Offering the program | 45 | 45 | 100% | All schools will be given attention for the programs
 | No. of Enrolment | 400 | 400 | 100% | All students will be given priority attention to the programs
 | No. of Activities Conducted | 7 | 0 | 0.00% | To be conducted on Q2 and Q3
IPEd (Indigenous Peoples Education Program) | No. of Schools Offering the program | 39 | 39 | 100% | All Schools will be given priority attention to the programs.
 | No. of Enrolment | 1626 |  |  | 
 | No. of Activities Conducted | 2 | 0 | 0.00% | Waiting for Fund to be downloaded
 | No. of Schools with program support funds (PSF) received | 0 | 0 | 0 | 0

## Slide 20
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
MG (Multigrade Education Program) | No. of Schools Offering the program | 2 | 2 | 100% | The two schools will be given priority program
 | No. of Enrolment | 123 | 123 | 100% | 
 | No. of Activities | 1 | 0 | 0.00% | To be conducted in Q2 MG Instruction for SHs
ALS (Alternative Learning System) | No. of Schools Offering the Program | 42 CLCs 3 ALS SHS 1 BJMP | 42 CLCs 3 ALS SHS 1 BJMP | 100% | All schools will be given the said program
 | No. of Enrolment | 1500 | BLP 52 A&E 109 A7E JHS 564 ALS SHS 183 |  | 39% of the mapped potential learners did not enroll in the ALS programs. Most of the school-aged children and youth as well as some OSY were enrolled in the formal school.
 | No. of Activities Conducted | 12 | 4 | 33.33% | Conduct of A&E Test Conduct of Regional ALS Encampment Procurement of supplies and materials in supports to teaching and learning Attendance of BAE Activity
 | No. of CAIs teachers with paid transportation and teaching aid allowance | 0 | 0 | 0.00% | There are no CIA in the Division
MEP (Madrasah Education Program) | No. of Schools Offering the Program | 1 | 1 | 100% | 
 | No. of Enrolment | 39 | 39 | 100% | 
 | No. of Asatidz paid | 3 | 3 | 100% | 
 | No. of Activities Conducted | 3 | 2 | 67% | 

## Slide 21
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
ALS (Alternative Learning System) | No. of Schools Offering the Program | 42 CLCs 3 ALS SHS 1 BJMP | 42 CLCs 3 ALS SHS 1 BJMP | 100% | 
 | No. of Enrolment | 1500 | BLP 52 A&E 109 A7E JHS 564 ALS SHS 183 |  | 39% of the mapped potential learners did not enroll in the ALS programs. Most of the school-aged children and youth as well as some OSY were enrolled in the formal school.
 | No. of Activities Conducted | 12 | 4 | 33.33% | Conduct of A&E Test Conduct of Regional ALS Encampment Procurement of supplies and materials in supports to teaching and learning Attendance of BAE Activity
 | No. of ALS teachers with paid transportation and teaching aid allowance | 20 | 20 | 100% | 
 | No. of CAIs teachers with paid transportation and teaching aid allowance | 0 | 0 | 0.00% | There are no CIA in the Division

## Slide 22
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
MEP (Madrasah Education Program) | No. of Schools Offering the Program | 1 | 1 | 100% | 
 | No. of Enrolment | 39 | 39 | 100% | 
 | No. of Asatidz paid | 3 | 3 | 100% | 
 | No. of Activities Conducted | 3 | 2 | 67% | Another activity will be conducted on Q2

## Slide 23
Quality
IO: Learners complete K-12 basic education, having successfully attained all learning standards that equip them with the necessary skills and attributes to pursue their chosen paths

## Slide 24
Elementary | SY 2022-2023 | SY 2023-2024 | SY 2024-2025
Elementary Completion Rate | 99.64 | 96.07 | 
Percentage of learners achieving nearly proficient or better in English | 25.67% | 26.34% | 32.11% (Transitioning Readers) – Source CRLA
Percentage of learners achieving nearly proficient or better in Numeracy | KS1: 11.237% (EOSY ALNAT 2022 – 2023) | KS1: 33.7% (EOSY RMA 2023 – 2024) | KS1: 27.69% (EOSY RMA 2024-2025)
Percentage of Grade 6 learners attaining nearly proficient level or better in stage 2 literacy standards | NDA | 38.78% (Phil-IRI) | 40.04% (Phil-IRI)
Percentage of Grade 6 learners attaining nearly proficient level or better in stage 2 numeracy standards | KS2: 13.252% (EOSY ALNAT 2022 – 2023) | KS2: 14.575% (EOSY ALNAT 2023 – 2024) | KS2: 21.388% (EOSY ALNAT 2024 – 2025)
KPIs (Three-Year Data)

## Slide 25
KPIs (Three-Year Data)
Secondary | SY 2022-2023 | SY 2023-2024 | SY 2024-2025
Secondary Completion Rate | 94.63 | 87.85 | None Yet
Percentage of Grade 10 learners attaining nearly proficient level or better in stage 3 literacy standards | NDA | 38.09% | 50.45%
Percentage of Grade 10 learners attaining nearly proficient level or better in stage 3 numeracy standards | KS3: 7.203% (EOSY ALNAT 2022 – 2023) | KS3: 3.987% (EOSY ALNAT 2023 – 2024) | KS3: 18.56% (EOSY ALNAT 2024 – 2025)
Percentage of Grade 12 learners attaining nearly proficient level or better in stage 4 SHS areas | NDA | NDA | NDA

## Slide 26
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
Learning Tools Equipment (LTE) – Science and Mathematics (SM) | No. of tools and equipment delivered | 1 | 0 | 0.00% | Documents are ongoing as to the Project Proposal, WFP, etc., and will be conducted/submitted for procurement in Q2
 | No. of learners benefiting the program | 3 Schools (SPNHS, SJIS. SLIS) | 0 | 0.00% | To be distributed in Q2

## Slide 27
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
Learning Tools Equipment (LTE) – Tech-Voc and Livelihood(TVL) Equipment | No. of tools and equipment delivered | 200 | 0 | 0.00% | Downloaded to ZAHS
 | No. of learners benefiting the program | 400 | 0 | 0.00% | To be procured by Q2
ELLN (Early Language Literacy and Numeracy) | No. of Activity Conducted | 2 | 0 | 0 | To be conducted on Q2
 | No. of teachers trained | 110 | 0 | 0.00% | To be conducted on Q2

## Slide 28
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
Textbooks (and Other Instructional materials) | No. of schools provided with textbooks/instructional materials | 39 | 0 | 0.00% | The sub aro has just arrived and will be implemented on Q2
NASBE (National Assessment Systems for Basic Education ) | No. of National Assessments conducted | 3 | 1 | 33.33% | NAT G12 and ELLNA to be conducted as per DM
 | No. of Activities conducted | 1 | 0 | 0.00% | To be conducted on Q2
FLO (Flexible Learning Options) | No. of Schools Provided with Learning Resources | 2 | 0 | 0.00% | Waiting for the 2025 Sub Aro

## Slide 29
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
ADM (Alternative Delivery Mode) | No. of Activities Conducted |  |  |  | 
ALSADM (Implementation of Alternative Learning and Delivery Mode Programs, including requirement of Learning Centers) | No. of Activities Conducted | 5 | 0 | 0 | Activities are scheduled on the second and fourth quarters
 | No. of materials procured | 60 | 0 | 0 | Still under procurement process (Procurement of supplies and materials in support to teaching and learning of ALS teachers and learners – Ink for Printers and Sign Pens)
 | No. of training/seminars/conferences attended | 17 | 2 | 11.76 | Only 1 division training-workshop for teachers and 1 BAE sponsored conference were attended by the teachers, EPSA, and Division Focal Person and select personnel for Quarter 1.
Journalism | No. of students participated in the National Press Conference | 8 (NSPC Qualifiers) |  |  | To participate in Q3
 | No. of Activities Conducted | 2 |  |  | To conduct in Q3

## Slide 30
resiliencY and well-being
IO: Learners are resilient and know their rights and have the life skills to protect themselves and claim their education-related rights from DepEd and other duty-bearers to promote learners’ well-being.

## Slide 31
PPA/Line Item | Physical |  |  |  | Reasons for over/underperformance
 | Performance Indicator | Physical Target (Annual) | Accomplishment (Q1) |  | 
 |  |  | Number | % | 
BEC (Basic Education Curriculum) | No. of learners participated in the activity (NLC) | 16,203 |  |  | To be participated in Q2
 | No. of Schools participated | 51 |  |  | To be participated in Q2
 | No. of teachers paid for their meal allowances | 374 |  |  | To be compensated through SC
 | No. of capacity building/orientation conducted | 4 |  |  | To be conducted in Q2
 | No. of learning materials procured/produced | 350 |  |  | To be procured in Q2

## Slide 32
Enabling Environment Performance Indicators

## Slide 33
Proportion of schools achieving the ideal ratio on:
Learning resources and learning materials (LRs and LMs) 1:1
Science and Math equipment (1:51)
Mathematics Manipulatives (1:8) for 39 Elem School
Multimedia package

## Slide 34
BCCs in Achieving the KPI Targets
EQUITY
Overlapping activities and other funds were downloaded only at the end of the year.

## Slide 35
BCCs in Achieving the KPI Targets
QUALITY
Limited Exposure of learners to technology based – instruction.
Need to intensify professional training/ development/seminar for teachers in beginning reading and numeracy instruction
Insufficient training to teachers in numeracy engagement
Low results in the ALNAT

## Slide 36
BCCs in Achieving the KPI Targets
RESILIENCE
Unwillingness of parents/guardians for their children to be included in the summer program
Advocating for the program to stakeholders.
WELL-BEING

## Slide 37
INITIATIVES
1. IRIGA Plus Program
2. Project LIBRO (Library Improvement for Better Reading Opportunities)
3. Project COSINE (Creating Optimum Synergical Innovations for Numeracy Enhancement)
4. Project BRACE ME (Bridging Reading Apprehensions via Contextualization and Community Engagement for a Meaningful Educational Experience)
5. Project GAINS (Gather Results on Learning Assessment and Initiative Intervention and Innovative Practices that Foster a Nurturing and Supportive Sustainable Environment)

## Slide 38
QUICK WINS
RFOT 2025 MUSABAQAH
2025 Regional Festival of Talents
2nd Place - Read-A-Thon Filipino
Nathalie Padayao,
Coach: Tanya Pandes
School Head: Ryan Ebron
School: La Anunciacion ES
2nd Place : Dish Gardening
Iriga Central School
2nd Place: Kasaysayan ng Pilipinas Quiz
Iriga Central School
6th Place: NumbeRace

## Slide 39
QUICK WINS
RFOT 2025 MUSABAQAH
2025 Regional Festival of Talents
2025 Sining Tanghalan Results
Overall Champion: SDO Iriga City
Folkdance - 1st Place
    Likhawitan - 1st Place
  Bayle sa Kalye - 2nd Place
  Sineliksik - 4th Place
  Direk ko, ganap mo - 4th Place
EPS Focal Person: CYNTHIA T. MONTAŇEZ

## Slide 40
2025 Thailand International Mathematical Olympiad (TIMO)

## Slide 41
2025 National Poster Making Contest in Celebration to the Araw ng Kagitingan
1st Prize Winner: Jeraldine Yia I. Buena
ZAHS
EPS Focal Person: FLORENIA C. TORALDE

## Slide 42
BEST PRACTICES
IRIGA Plus Program

## Slide 43: WAYS TO MOVE FORWARD
Continuation or enhancement of IRIGA Plus Program and will have a midyear and EOSY validation.
Intensifying the priority projects of each learning area along literacy and numeracy
Sense of urgency along with the sense of doability for PPAs.
Intensify the project along reading program

## Slide 45
CY 2025 1ST QUARTER BOTTLENECKS, CONSTRAINTS, AND CHALLENGES (BCCs) AND THE PRESENT STATUS

## Slide 46
BOTTLENECKS, CONSTRAINTS, AND CHALLENGES (BCCs)/ISSUES | INSTRUCTIONS/ AGREEMENT | ACTION RESPONSES | STATUS

## Slide 47
Operational and Policy Issues and Recommendations/Actions Needed from Central Office
PPAs | Operational or Policy Issue | Recommendation of the RO | Decision and Actions Needed from CO